## Sheet1
Functionality | Date
Build Zero
Iteration Plan | Week 1 through Week 2
Student Login Functionality - iOS application
Design the app UI - Static
Design the Web application UI - Static
Unit Testing for the developed modules
Build One
Design tables in the Back4app database | Week 3 through Week 4
Add dummy data onto the database
Developing UI for the scanner functionality in iOS device
Developing the QR generator code functionality in Web application
Manage students method
Manage courses method
Database connectivity to both iOS and Web application
Unit Testing for the developed modules
Demo the product to the Client
Build two
Data retrieval onto the course page - Instructor | Week 5 through Week 6
Data retrieval of Instructor details
Logout functionality
Can't navigate to previous page when the Instructor logsout
Feedback in instructor perspective
Data retrieval of attendance data - Instructor
Unit Testing
Add courses
Remove courses
Logic for total attendance percentage
View attendance details of Instructor on day to day basis
Unit Testing for the developed modules
Build Three
Capture the QR code | Week 7 through Week 8
Retrieve student details
Edit student details
View his attendance in all courses
View courses in student perspective
Persistent login functionality - Student
View attendance details of Student on day to day basis
Storing the QR code unique string onto the database
Editing the Instructor details
Conditional retrieval of courses and attendance data.
Alternate login if Instructor forgets his/her username
Alternate login if student forgets his/her username
Password Encryption
Feedback for Student functionalities
Unit Testing for the developed modules
Build Four
Integration Testing | Week 9