## Week1
Daily Stand-up Meeting Report
Week: June 12 - June 16
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali | 1) | 1) Introducing each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Client meeting Minutes
| 2) | 2) Strengths and Weakness | 2) Discussion on the Team Name | 2) Client Requirements | 2) Different approaches for the project
| 3) | 3) None | 3) None | 3) None | 3) Clarity on client specifications
Rohith Babu Sadhu | 1) | 1) Introducing each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Requirements of the project
| 2) | 2) Creating Google Drive for sharing Information | 2) Discussion on the Team Name | 2) Requirements specified by client | 2) Different approaches for the project
| 3) | 3) None | 3) None | 3) None. | 3) Requirements are ambigious
Sri Sai Ram Kumar Mamidala | 1) | 1) Introducing each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Designed Team Logo and project over view document
| 2) | 2) Strengths and Weakness | 2) Roles and Responsibilities | 2) Worked on Team logo and outline of the project | 2) Issues in the client requirements
| 3) | 3) None | 3) None | 3) None | 3) Should get clarity on the requirments
Vipul Reddy Madadi | 1) | 1) Introducing each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Team meeting minutes document
| 2) | 2) Strengths and Weakness | 2) Discussion on the Team Name | 2) Client Requirements | 2) Issues in the client requirements
| 3) | 3) None | 3) None | 3)None | 3) None
Vamsi Devalla | 1) | 1) Introducing each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Stand-up meeting Documentation
| 2) | 2) Created Google docs and shared with others | 2) Roles and Responsibilities | 2) Creation of Repository for commiting the project updates | 2) Different approaches for the project
| 3) | 3) None | 3) None | 3) None | 3) Doubts with some requirements
SubbaReddy Pothireddy | 1) | 1) Introduced to each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Worked on designing team meeting document
| 2) | 2) Creating whats app group to share information | 2) Roles and Responsibilities | 2) Requirements of the project | 2) Issues in the client requirements
| 3) | 3) None | 3) None | 3) None | 3) None
Shankar Rao Vallapurapu | 1) | 1) Introduced to each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Worked on team logo
| 2) | 2) Created Whatsapp group to share information | 2) Roles and Responsibilities | 2) Requirements specified by Client | 2) Issues in the client requirements
| 3) | 3) None | 3) None | 3)None | 3) Some requirements are ambiguous
Note:
1. Work done till now? 2. Discussion on what part? 3. Difficulties faced till now?

## Week2
Daily Stand-up Meeting Report
Week: June 19 - June 23
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali | 1) Approaches for the project | 1) Team meeting minutes | Core Functionalities
| 2) Finalizing an approach and establishing next teem meeting | 2) Core functionalities of the project | Use Case for Student
| 3) approach selection | 3)
Rohith Babu Sadhu | 1) Approaches for the project | 1) Client meeting notes | Requirement Documentation
| 2) Finalizing an aproach and issues to talk with the client | 2) Core functionalities of the project | Use Case for Student
| 3) approach selection | 3)
Sri Sai Ram Kumar Mamidala | 1) Approaches for the project | 1) Issues specifications
| 2) Finalizing an approach | 2) Non functional requirements of the project
| 3) Requirements selection | 3)
Vipul Reddy Madadi | 1) Reviewing the Requirements Document | 1) Requirements document
| 2) Issues regarding the approach | 2) Non functional requirements
| 3) none | 3)
Vamsi Devalla | 1) Approaches for the project | 1) Team meeting document and requirements.
| 2) Issues regarding the testing of the approach | 2) Core functionalities of the project
| 3) issues on quality of the project | 3)
SubbaReddy Pothireddy | 1) Requirements for the Project | 1) Documenting issues
| 2) Issues regarding the approach | 2) Non functional requirements of the project
| 3) None | 3)
Shankar Rao Vallapurapu | 1) Tools for the approach | 1) Review of the approaches
| 2) Tools available for the development of the selected approach | 2) Non functional requirements of the project
| 3) none | 3)
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week3
Daily Stand-up Meeting Report
Week: June 26 - June 30
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali
Rohith Babu Sadhu
Sri Sai Ram Kumar Mamidala
Vipul Reddy Madadi
Vamsi Devalla
SubbaReddy Pothireddy
Shankar Rao Vallapurapu
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week4
Daily Stand-up Meeting Report
Week: July 03 - July 07
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali
Rohith Babu Sadhu
Sri Sai Ram Kumar Mamidala
Vipul Reddy Madadi
Vamsi Devalla
SubbaReddy Pothireddy
Shankar Rao Vallapurapu
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week5
Daily Stand-up Meeting Report
Week: July 10 - July 14
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali
Rohith Babu Sadhu
Sri Sai Ram Kumar Mamidala
Vipul Reddy Madadi
Vamsi Devalla
SubbaReddy Pothireddy
Shankar Rao Vallapurapu
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week6
Daily Stand-up Meeting Report
Week: July 17 - July 21
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali
Rohith Babu Sadhu
Sri Sai Ram Kumar Mamidala
Vipul Reddy Madadi
Vamsi Devalla
SubbaReddy Pothireddy
Shankar Rao Vallapurapu
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week7
Daily Stand-up Meeting Report
Week:
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali
Rohith Babu Sadhu
Sri Sai Ram Kumar Mamidala
Vipul Reddy Madadi
Vamsi Devalla
SubbaReddy Pothireddy
Shankar Rao Vallapurapu
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week8
Daily Stand-up Meeting Report
Week:
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali
Rohith Babu Sadhu
Sri Sai Ram Kumar Mamidala
Vipul Reddy Madadi
Vamsi Devalla
SubbaReddy Pothireddy
Shankar Rao Vallapurapu
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week9
Daily Stand-up Meeting Report
Week:
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali
Rohith Babu Sadhu
Sri Sai Ram Kumar Mamidala
Vipul Reddy Madadi
Vamsi Devalla
SubbaReddy Pothireddy
Shankar Rao Vallapurapu
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?