## Week1
Daily Stand-up Meeting Report
Week: June 12 - June 16
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali | 1) | 1) Introducing each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Client meeting Minutes
| 2) | 2) Strengths and Weakness | 2) Discussion on the Team Name | 2) Client Requirements | 2) Different approaches for the project
| 3) | 3) None | 3) None | 3) None | 3) Clarity on client specifications
Rohith Babu Sadhu | 1) | 1) Introducing each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Requirements of the project
| 2) | 2) Creating Google Drive for sharing Information | 2) Discussion on the Team Name | 2) Requirements specified by client | 2) Different approaches for the project
| 3) | 3) None | 3) None | 3) None. | 3) Requirements are ambigious
Sri Sai Ram Kumar Mamidala | 1) | 1) Introducing each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Designed Team Logo and project over view document
| 2) | 2) Strengths and Weakness | 2) Roles and Responsibilities | 2) Worked on Team logo and outline of the project | 2) Issues in the client requirements
| 3) | 3) None | 3) None | 3) None | 3) Should get clarity on the requirments
Vipul Reddy Madadi | 1) | 1) Introducing each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Team meeting minutes document
| 2) | 2) Strengths and Weakness | 2) Discussion on the Team Name | 2) Client Requirements | 2) Issues in the client requirements
| 3) | 3) None | 3) None | 3)None | 3) None
Vamsi Devalla | 1) | 1) Introducing each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Stand-up meeting Documentation
| 2) | 2) Created Google docs and shared with others | 2) Roles and Responsibilities | 2) Creation of Repository for commiting the project updates | 2) Different approaches for the project
| 3) | 3) None | 3) None | 3) None | 3) Doubts with some requirements
SubbaReddy Pothireddy | 1) | 1) Introduced to each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Worked on designing team meeting document
| 2) | 2) Creating whats app group to share information | 2) Roles and Responsibilities | 2) Requirements of the project | 2) Issues in the client requirements
| 3) | 3) None | 3) None | 3) None | 3) None
Shankar Rao Vallapurapu | 1) | 1) Introduced to each other. | 1) knowing team members | 1) Team Name and individual Roles | 1) Worked on team logo
| 2) | 2) Created Whatsapp group to share information | 2) Roles and Responsibilities | 2) Requirements specified by Client | 2) Issues in the client requirements
| 3) | 3) None | 3) None | 3)None | 3) Some requirements are ambiguous
Note:
1. Work done till now? 2. Discussion on what part? 3. Difficulties faced till now?

## Week2
Daily Stand-up Meeting Report
Week: June 19 - June 23
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali | 1) Approaches for the project | 1) Team meeting minutes | Core Functionalities | core functionalities | use case diagram for student
| 2) Finalizing an approach and establishing next teem meeting | 2) Core functionalities of the project | Core Functionalities of the project | Use case diagram for student | use case diagram for student
| 3) approach selection | 3) none | none | none | none
Rohith Babu Sadhu | 1) Approaches for the project | 1) Client meeting notes | Requirement Documentation | core functionalities | use case diagram for student
| 2) Finalizing an aproach and issues to talk with the client | 2) Core functionalities of the project | Core Functionalities of the project | Use case diagram for student | use case diagram for student
| 3) approach selection | 3) none | none | none | none
Sri Sai Ram Kumar Mamidala | 1) Approaches for the project | 1) Issues specifications | Issues specification | core functionalities | use case diagram for instructor
| 2) Finalizing an approach | 2) Non functional requirements of the project | Core Functionalities of the project | use case diagram for instructor | use case diagram for instructor
| 3) Requirements selection | 3) none | none | none | none
Vipul Reddy Madadi | 1) Reviewing the Requirements Document | 1) Requirements document | Requirement Documentation | purpose of the project | scope of project
| 2) Issues regarding the approach | 2) Non functional requirements | Purpose of the project | scope of the project | functional requirements documentation
| 3) none | 3) none | none | none | none
Vamsi Devalla | 1) Approaches for the project | 1) Team meeting document and requirements. | Minutes of meeting | core functionalities | use case diagram for admin
| 2) Issues regarding the testing of the approach | 2) Core functionalities of the project | Core Functionalities of the project | use case diagram for admin | use case diagram for admin
| 3) issues on quality of the project | 3) none | none | none | none
SubbaReddy Pothireddy | 1) Requirements for the Project | 1) Documenting issues | Stand-up-Meeting | non functional requirements | functional requirements documentation
| 2) Issues regarding the approach | 2) Non functional requirements of the project | Non functional requirements of the project | functional requirements | functional requirements documentation
| 3) None | 3) none | none | none | none
Shankar Rao Vallapurapu | 1) Tools for the approach | 1) Review of the approaches | Minutes of meeting | scope of the project | purpose of the project
| 2) Tools available for the development of the selected approach | 2) Non functional requirements of the project | Scope of the project | purpose of the project | functional requirements documentation
| 3) none | 3) none | none | none | none
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week3
Daily Stand-up Meeting Report
Week: June 26 - June 30
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali | use case diagram for student | use case diagrams for student | worked on test plan and test suits | ER diagram for the student | ER diagram for the student
| modification of use case diagrams for students module | working on test plan and test suits | mid term presentation | develop ER diagram for student module | develop ER diagram for the student module
Rohith Babu Sadhu | use case diagram for student | use case diagrams for student | requirements specification document | ER diagram for the student | ER diagram for the student
| modification of use case diagrams for students module | worked on requirements specification document | mid term presentation | design the ER diagram for the student module | design the ER diagram for the student module
Sri Sai Ram Kumar Mamidala | use case diagram for instructor | use case diagrams for instructor | use case description | ER diagram for the instructor | Prototype student module
| modification of use case diagrams for instructors module | use case diagram description for the instructor | mid term presentation | Develop ER diagram for instructor module | continuation of prototyping for student module with shankar
Vipul Reddy Madadi | Requirements documentation | worked on requirements specification document | integrating scope statement | dependencies of the project | dependencies of the project
| working on requirements document | integrating the scope statement | mid term presentation | Work on dependecies and integrated in requirements documents | work on dependencies and integrated in requirements document
Vamsi Devalla | use case diagram for admin | use case diagram description for the admin | worked on project management plan | ER diagram for the instructor | ER diagram for the instructor
| modification of the use case for admins point of view | worked on project management plan document | mid term presentation | design ER diagram for the instructor module | develop ER diagram for the instructor module
SubbaReddy Pothireddy | Requirements documentation | working on requirements document | issue management plan | ER diagram for admin | Issue management plan
| working on requirements document | issue management document | mid term presentation | develop ER diagram for admin point of view | documenting the issues in ER diagram
Shankar Rao Vallapurapu | use case diagram for admin | use case diagram for admin | mid term presentation | prototype the student module | ER diagram for the instructor
| modification of use case from admin point of view | presentation for the midterm submission | mid term presentation | Start prototyping the student module | develop ER diagram for the instructor module
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week4
Daily Stand-up Meeting Report
Week: July 03 - July 07
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali | develop ER diagram for the student module | core functionalities for prototyping | initial prototype of the instructor's module | identifying the practical issues while prototyping | prototyping the instructor's module
| Identfying the key features for instructor's view for prototyping | Prototyping system from instructor's point of view | Identifying the issue of the core features while prototyping the instructors module | Prototyping system from instructor's point of view considering all the issues | updating the Issue management document respectively
|  | none | none | detailing in the student view prototype | none
Rohith Babu Sadhu | design the ER diagram for the student module | core functionalities for prototyping | initial prototype of the instructor's module | identifying the practical issues while prototyping | prototyping the instructor's module
| Identfying the key features for instructor's view for prototyping | Prototyping system from instructor's point of view | Identifying the issue of the core features while prototyping the instructors module | Prototyping system from instructor's point of view considering all the issues | Updating the minutes in the stand-up-meeting document
|  | none | detailing the constraints | none | none
Sri Sai Ram Kumar Mamidala | continuation of prototyping for student module with shankar | core functionalities for prototyping | initial prototype of the students module | identifying the smaller issues while prototyping | prototyping the students module
| Identfying the key features for Students view for prototyping | Prototyping system from students point of view | Identifying the issue of the core features while prototyping the students module | Prototyping system from students point of view considering all the issues | Updating the team meeting document
|  | none | detailing the constraints | detailing in the admins view | none
Vipul Reddy Madadi | work on dependencies and integrated in requirements document | Test cases for the document | updating the test cases which are obtained while prototyping | identifying the smaller issues while prototyping | test case document
| Test cases for the document | Test cases for the document | updating the test cases which are obtained while prototyping | Test cases for the document | Work Breakdown structure
|  | none | none | none | none
Vamsi Devalla | develop ER diagram for the instructor module | core functionalities for prototyping | initial prototype for the admin's prototype | identifying the smaller issues while prototyping | prototpying the admin's module
| Identfying the key features for admin's view for prototyping | prototyping the system from the admin's point of view | Identifying the issue of the core features while prototyping the admin's module | prototyping the system from the admin's point of view considering all the issues | Work Breakdown structure
|  | none | none | detailing the constraints in the system | none
SubbaReddy Pothireddy | documenting the issues in ER diagram | core functionalities for prototyping | initial prototype for the admin's prototype | identifying the smaller issues while prototyping | prototyping the admin's module
| Identfying the key features for admin's view for prototyping | prototyping the system from admin's point of view | Identifying the issue of the core features while prototyping the admin's module | prototyping the system from admin's point of view considering all the issues | Issue management document
|  | none | issues management document | system constraints | none
Shankar Rao Vallapurapu | develop ER diagram for the instructor module | core functionalities for prototyping | initial prototype for the sttudents view | identfying the smaller issues while prototyping | prototyping the students module
| Identfying the key features for students view for prototyping | prototyping the system from the students point of view | Identifying the issue of the core features while prototyping the students module | prototyping the system from the students point of view considering all the issues | Updating requirements document with a test case for each requirement
|  | none | none | none | none
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week5
Daily Stand-up Meeting Report
Week: July 10 - July 14
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali | determine non functional requierments | documented non functional requierments | determined external interfaces | determined external interfaces | documenting the external interfaces
| determined the non functional requirements focusing on availability | documented the non functional requirements about availability | determined the external interfaces specifying login subsystem | determined the external interfaces specifying signup subsystem | documeting login and signup subsystem external interfaces
Rohith Babu Sadhu | determine non functional requierments | determine non functional requierments | documented non functional requierments | determined external interfaces | documenting external interfaces
| determined the non functional requirements focusing on reliability | determined the non functional requirements focusing on security | documented the non functional requirements about reliability and security and integrated the documents | determined the external interfaces specifying interfaces subsystem | documenting the external interfaces specifying interfaces subsystem
Sri Sai Ram Kumar Mamidala | determined the logical database requirements | determined the logical database requirements | determined the logical database requirements | documenting the logical database requirements | documenting the logical database requirements
| determined the file format of how the information is used by various functions | determined the file format of how frequently we use and also the accessing capabilities | determined the accessing capabilities of the file format | documenting all the logical database requirements of the file format | documenting and integrating all these requirements.
Vipul Reddy Madadi | determined the performance requirements | determined the performance requirements | determined the performance requirements | document the performance requirements | document the performance requirements
| determined the performance requirements such as increasing and decreasing the reliability | determined the performance requirements such as increasing and decreasing the reliability | determined the performance requirements such as increasing and decreasing the reliability | document the performance requirements such as increasing and decreasing the reliability | document the performance requirements such as increasing and decreasing the reliability
Vamsi Devalla | determined the design constraints | determined the design constraints | documenting the design constraints | documenting the design constraints | completing the ghantt charts
| determined the design constraints focusing on system interfaces | determined the design constraints focusing on quality issues and system modifications | documented the design constraints on system interfaces | documented the design constraints on quality issues and system modifications | completed the ghantt charts for the WBS of the project.
SubbaReddy Pothireddy | determined the design constraints | determined the design constraints | determined the design constraints | documenting the design constraints | documenting the design constraints
| determined the design constraints focusing on user interface and human factors | determined the design constraints focusing on hardware considerations | determined the design constraints focusing on performance characteristics | documented the design constraints on hardware considerations | documented the design constraints on performance characteristics
Shankar Rao Vallapurapu | determined the logical database requirements | determined the logical database requirements | determined the logical database requirements | documenting the logical database requirements | documenting the logical database requirements
| determined the entities and relationships and their accessibilities | determined the security aspects of the integrity constraints | determined the data retention requirements | documenting all the logical database requirements related to accessibility | documenting all the logical database requirements related to security issues and also integrated all the documents
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week6
Daily Stand-up Meeting Report
Week: Sep 4 - Sep 8
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali |  | review of the documentation | iteration plan proposal | roles of individualts | core functionalities
| review of the entire documentation | working for the project iteration plan | discussing what to do in the project either web app or the stand alone application | discussing the core functionalities of the project | dividing the project modules
Rohith Babu Sadhu |  | review of the documentation | iteration plan proposal | roles of individualts | core functionalities
| review of the entire documentation | working for the project iteration plan | discussing what to do in the project either web app or the stand alone application | discussing the core functionalities of the project | dividing the project modules
Sri Sai Ram Kumar Mamidala |  | review of the documentation | iteration plan proposal | roles of individualts | core functionalities
| review of the entire documentation | working for the project iteration plan | discussing what to do in the project either web app or the stand alone application | discussing the core functionalities of the project | dividing the project modules
Vipul Reddy Madadi |  | discussion on the project main features | iteration plan proposal | roles of individualts | core functionalities
| discussion on the project main features | working for the project iteration plan | discussing what to do in the project either web app or the stand alone application | discussing the core functionalities of the project | dividing the project modules
Vamsi Devalla |  | review of the documentation | iteration plan proposal | roles of individualts | core functionalities
| review of the entire documentation | working for the project iteration plan | discussing what to do in the project either web app or the stand alone application | discussing the core functionalities of the project | dividing the project modules
SubbaReddy Pothireddy |  | discussion on the project main features | iteration plan proposal | roles of individualts | core functionalities
| discussion on the project main features | working for the project iteration plan | discussing what to do in the project either web app or the stand alone application | discussing the core functionalities of the project | dividing the project modules
Shankar Rao Vallapurapu |  | discussion on the project main features | iteration plan proposal | roles of individualts | core functionalities
| discussion on the project main features | working for the project iteration plan | discussing what to do in the project either web app or the stand alone application | discussing the core functionalities of the project | dividing the project modules
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week7
Daily Stand-up Meeting Report
Week: Sep 11 - Sep 15
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali | dividing the project modules | discussion on the prototypes |  | IOS application | discussion on the stand alone to web app
| discussing the prototypes of the project | discussion on the IOS application | discussion on the IOS application | change of plans from stand alone application to web app | finalizing the web application and discussion of the language
| none | none | none | difficult to develop an stand alone application | none
Rohith Babu Sadhu | dividing the project modules | discussion on the prototypes |  | IOS application | discussion on the stand alone to web app
| discussing the prototypes of the project | discussion on the IOS application | discussion on the IOS application | change of plans from stand alone application to web app | finalizing the web application and discussion of the language
| none | none | none | difficult to develop an stand alone application | none
Sri Sai Ram Kumar Mamidala | dividing the project modules | discussion on the prototypes |  | IOS application | discussion on the stand alone to web app
| discussing the prototypes of the project | discussion on the IOS application | discussion on the IOS application | change of plans from stand alone application to web app | finalizing the web application and discussion of the language
| none | none | none | difficult to develop an stand alone application | none
Vipul Reddy Madadi | dividing the project modules | discussion on the prototypes |  | IOS application | discussion on the stand alone to web app
| reviewing the iteration plan | working on the stand alone application | working on the stand alone application | change of plans from stand alone application to web app | finalizing the web application and discussion of the language
| none | none | none | difficult to develop an stand alone application | none
Vamsi Devalla | dividing the project modules | discussion on the prototypes |  | IOS application | discussion on the stand alone to web app
| discussing the prototypes of the project | working on the stand alone application | working on the stand alone application | change of plans from stand alone application to web app | finalizing the web application and discussion of the language
| none | none | none | difficult to develop an stand alone application | none
SubbaReddy Pothireddy | dividing the project modules | discussion on the prototypes |  | IOS application | discussion on the stand alone to web app
| reviewing the iteration plan | working on the stand alone application | working on the stand alone application | change of plans from stand alone application to web app | finalizing the web application and discussion of the language
| none | none | none | difficult to develop an stand alone application | none
Shankar Rao Vallapurapu | dividing the project modules | discussion on the prototypes |  | IOS application | discussion on the stand alone to web app
| reviewing the iteration plan | working on the stand alone application | working on the stand alone application | change of plans from stand alone application to web app | finalizing the web application and discussion of the language
| none | none | none | difficult to develop an stand alone application | none
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week8
Daily Stand-up Meeting Report
Week: Sep 18 - Sep 22
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali |  | UI for the IOS application | UI for the IOS application | Discussion on the database | database discussion
| Developing the UI for the project | developing the UI for the web application | discussion the database | discussion on the database either back4app or firebase | finalizing the UI for the IOS application
| none | developing the UI for QR scanning page | retrieving the information from the database | none | none
Rohith Babu Sadhu |  | UI for the IOS application | UI for the IOS application | Discussion on the database | database discussion
| Developing the UI for the project | developing the UI for the web application | discussion the database | discussion on the database either back4app or firebase | finalizing the UI for the IOS application
| none | developing the UI for the QR generating page | retrieving the information from the database | none | none
Sri Sai Ram Kumar Mamidala |  | UI for the IOS application | UI for the web app | Discussion on the database | database discussion
| Developing the UI for the project | developing the UI for the web application | discussion the database | discussion on the database either back4app or firebase | finalizing the UI for the IOS application
| none | developing the UI for the registration page | retrieving the information from the database | none | none
Vipul Reddy Madadi |  | UI for the IOS application | UI for the web app | Discussion on the database | database discussion
| Developing the UI for the project | developing the UI for the web application | discussion the database | discussion on the database either back4app or firebase | finalizing the UI for the web application
| none | none | retrieving the information from the database | none | none
Vamsi Devalla |  | UI for the IOS application | UI for the web app | Discussion on the database | database discussion
| Developing the UI for the project | developing the UI for the web application | discussion the database | discussion on the database either back4app or firebase | finalizing the UI for the web application
| none | developing the UI for the courses page | retrieving the information from the database | none | none
SubbaReddy Pothireddy |  | UI for the IOS application | UI for the IOS application | Discussion on the database | database discussion
| Developing the UI for the project | developing the UI for the web application | discussion the database | discussion on the database either back4app or firebase | finalizing the UI for the web application
| none | none | retrieving the information from the database | none | none
Shankar Rao Vallapurapu |  | UI for the IOS application | UI for the IOS application | Discussion on the database | database discussion
| Developing the UI for the project | developing the UI for the web application | discussion the database | discussion on the database either back4app or firebase | finalizing the UI for the web application
| none | none | retrieving the information from the database | none | none
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?

## Week9
Daily Stand-up Meeting Report
Week: Sep 25 - Sep 29
Project Name: Student Attendence Tracking
Team Name: Code Green
| Monday | Tuesday | Wednesday | Thursday | Friday
Sirisha Vanamali
Rohith Babu Sadhu
Sri Sai Ram Kumar Mamidala
Vipul Reddy Madadi
Vamsi Devalla
SubbaReddy Pothireddy
Shankar Rao Vallapurapu
Note:
1. Work done till now ? 2. Working on what work? 3.Difficulties faced till now?